## Sheet1
|  |  | Work Plan |  | Jan | [16 empty] | Feb
[5 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
|  |  | Software Design Stage | Activity Diagram/Use Case
CRC cards
Class diagram
GUI Conceptual Design
|  |  | Software Implementation Stage | Coding - main, manager, menucard
Test
14-20 | 21-27 | 28-3
Week 1 | Week 2 | Week 3

## Sheet2
Work Plan
|  | 14-20 Jan | 21-27 Jan | 28-3 Feb | 4-10 Feb | 11-17 Feb | 18-21 Feb
| Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Software Design Stage | Activity/Use Case diagram
CRC cards
Class diagram
GUI Conceptual Design
Software Implementation Stage | Coding - main/ manager/ itemslist
Coding - GUI/Order/Orderlist/Discount
Testing / Bug fixing
Report / bi-weekly meetings